## Sheet1
No. | Issues / Suggestion / Changes Request | Status | Comments | Update | ARE&M response | Status | Updates / Reasons /Suggestions
1 | NCR waiting for Close option should be moved to reports option in Process HOD ID, At present available in Home position. | Completed |  |  | OK
2 | ⁠Manual e-mails and Top management manual e-mails options not available. | Pending / Need Clarification |  | Need Update on this | OK
3 | All dashboard graphs/data should be displayed by selecting the audit schedule number. | Completed | Recent Schedule will be default |  | OK
4 | User details should be displayed in top corners. | Completed |  |  | OK
5 | Justification for classification dialogue box not displayed in EDC submission window -Auditee ID. | Completed |  |  | OK
6 | ⁠In create NCR option, Minor/Major NCR type should be disabled when we select suggestion – Auditor ID. | Completed |  |  | OK
7 | ⁠In auditor check list, Check point additions, modification and deletion options should be required – Map this option in Process admin ID (updated check list should be displayed in auditor ID). | Pending / Need Clarification | Need an options in admin panel to edit, delete and add the requirements | Planning to do once get confirmation Checklist Format | Clarity given on check list preparation -UP | Pending | Work in Progress
8 | ⁠In create user, Forgot password options required for password recreation by sending a password reset link to mail. | Completed |  |  | Forgot password option is required in user credential entry screen | Completed
9 | Plant name and standard and audit schedule modification, deletion options are required in Process admin ID. | Completed |  |  | Plant name, standard and audit schedule should not be saved, if the same data is available. | Pending | Cant't make Plant and Audit Standard name now since there are already some duplicates. will do this at the time of production
10 | ⁠Users delete options required in auditor, auditee and HOD list – Delete option required in process admin ID. | Completed |  |  | OK
11 | ⁠Process auditor list should be maintained in FIFO basis ( first generated user should be first row in list). | Completed |  |  | OK
12 | Auditee & audit representative list should be maintained plant wise in list. | Completed |  |  | OK
13 | ⁠Date of joining column should be referred as joining date in organization, not a user creation date. | Completed | Provided "Joined On" Field in Create User Form |  | OK
14 | ⁠Auditee representative needs to be included in role category -user creation page. | Completed |  |  | OK
15 | In schedule preparation, there is an 2023-2024 mentioned. | Completed |  |  | OK
16 | ⁠User creation option not required in Process HOD ID – Required in Process admin. | Completed |  |  | OK
17 | ⁠In create audit schedule – select schedule and audit based on options should be merged. | Completed |  |  | OK
18 | NCR number sequence should be modified as per the existing portal sequence. | Pending | Bussineess Unit need to be added in plant creation page, bussiness unit name should reflect in ncr number and audit schedule |  | Schedule reference number and NCR number should be inline with existing portal | Completed
19 | ⁠In create NCR window, Shifts need to be ensured (First shift missing). | Completed | Add one more shift Morning in select shift |  | OK
20 | In create NCR window, page no. should be entered as 01 of 02 ( At present alphabets are unable to enter). | Completed |  |  | OK
21 | ⁠In create NCR window, Paragraph numbers should be entered as 4.1.1 (example) – at present, special characteristics are unable to enter. | Completed |  |  | OK
22 | Comment options not required in close audit window -Process auditor. | Completed | Tabel with an close audit button with tootla major / minor ncr and sugeestions |  | OK
23 | ⁠Data mapping mismatch observed in NCR report. | Completed |  |  | Yet to verify, data not yet listing in NCR report
24 | Data overlapping observed with another dialogue box in NCR report. | Completed | NCR Report view text overlapping need to be fixed |  | Overlapping not observed | Completed
25 | ⁠ ⁠EDC given date not correct in NCR report, | Completed |  |  | EDC given date not correct, screenshot shared | Completed | New EDC Should be update in case new edc request.NCR Report Expected Date of Completion Given Date when edc submitted
26 | ⁠In EDC submission window, justification for the classification dialogue box not available -Auditee. | Completed |  |  | OK
27 | ⁠In EDC submission window, Root cause dialogue box need to be added. | Completed |  |  | (Dialogue box sequence) Non-conformity lot diposal, correction, root cause and corrective and preventive action sequence should be ensured as per existing | Completed | 1. Non-comfirmity lot disposal 2. Correction 3. Root cause 4. Corrective actions prevenion
28 | ⁠Dashboard details not updating in Home page -Process HOD ID. | Completed | Need to update in real time in dashboard |  | Fetching the data as per the process audit schedule -OK | Completed
29 | In request for follow-up audit window, Request for EDC extension approval option not required during the NCR with in the EDC. | Completed |  |  | EDC extension button was showing even NCR was in with in EDC | Completed
30 | ⁠Root cause, correction and corrective actions need to be added in assign follow-up audit window. | Completed |  |  | (Dialogue box sequence) Non-conformity lot diposal, correction, root cause and corrective and preventive action sequence should be rearranged as per the EDC submission window (Existing) | Completed | same as 27
31 | ⁠Process HOD rejected the follow-up audit request approval. After rejection, particular NCR was not visible in Auditee ID again. | Completed | Rejected ncr need to visible in Auditee ID |  | Those NCR will shows in Rejected NCR list in auditee ID. But, we need feasibility to modify the data | Completed | Spearate modal for EDC Submission
32 | ⁠In create NCR, * marks need to be remove for Doc No., Page No., Paragraph No dialogue box. | Completed |  |  | OK
33 | ⁠Error message should be displayed, if any required options are not selected. But, it showing as successfully done. | Completed |  |  | screeshot shared. Without required option selection the actions are completed | Completed
34 | ⁠NCR numbers should not be available in follow-up auditor ID, once he submitted the follow-up audit observations. | Completed |  |  | OK
35 | EDC and ADC dates are nor displaying in detailed report. | Completed |  |  | data entered by auditee and followup auditor and process HOD was not showing. Some other field also data missing. | Completed
36 | ⁠Pop-up mail communication formats to be improved and additional data to be included as per our recent discussion. | Completed |  | Planning to do once get update about popup mail (2) | data missmatch and data missing observed in some communication. | Completed
| Request for EDC extension option should not required, when it was in with the specified date |  |  |  | Request for EDC extension option should not required, when it was in with the specified date | Completed